## Sheet1
Materials, Traps, Weapons, Minor Objectives will probably have definitive start and end tasks. Player and AI classes will probably be continuously updated to integrate the other objects.
Week | Development Plan | Assigned To | Test and Demonstration Plan
1/24 - 1/31
Set up an Unreal Engine project with source control
|  | Kenny | Created and initialized UE project. Pushed to GitHub
|  | Tony | Pulled project, added sphere to project. Pushed to GitHub.
|  | Nick | Pulled project, modified C++ files. Pushed to GitHub.
|  | Roger | Pulled project, added pillars to project. Pushed to GitHub.
| Make a bird's eye view of the level. | Nick
1/31 - 2/7
| Start building the level according to the bird's eye view. | Nick | Game demonstration.
| Add skeletal mesh to player pawn; update project defaults to select game mode and pawn. | Tony | Screenshot of skeletal mesh attached to player pawn.
| Make player pawn move around and jump. | Roger | Game demonstration.
| Create a material actor. Allow player to interact w/ material. | Kenny | Game demonstration.
| Create AI pawn. Have it follow player. | Kenny | Game demonstration.
2/7 - 2/14
| Create more variety of materials. Create material set for game. |  | Screenshot or code
| Add functionality to check if material is brought to a specific location. |  | Game demonstration
| Have AI scout prioritize locations with materials. |  | Game demonstration
| Add details, lighting, etc. to map. |  | Game demonstration
2/14 - 2/21
Finish Material, Start Minor Objective
2/21 - 2/28
2/28 - 3/4
3/4 - 3/7
Finish Minor Objective, Start Trap
3/7 - 3/14
3/14 - 3/21
3/21 - 3/28
Finish Trap, Start Weapon
3/28 - 4/4
4/4 - 4/11
4/11 - 4/18
Finish Game
4/18 - **4/23**
Test Final Game, download to other PC's/laptops, determine how to present at conference