## Sheet1
Materials, Traps, Weapons, Minor Objectives will probably have definitive start and end tasks. Player and AI classes will probably be continuously updated to integrate the other objects.
Week | Development Plan | Assigned To | Test and Demonstration Plan
1/24 - 1/31
| Set up an Unreal Engine project with source control | Everyone
Mapping: Develop a bird's eye view for a map layout that makes sense with our game. Include locations for spawning, materials, minor objectives, and weapon crafting
Player: Create simple Player Pawn and Player Controller. Attach PlayerController to PlayerPawn.
AI: Create simple AI Pawn and AI Controller.
Game Mode: Create simple Game Mode. If AI Pawn is dead or Player lives = 0, end game.
1/31 - 2/7
Mapping: Start building the level according to the bird's eye view. Expand the ground, add walls to mimic the design.
Player: Create data structure for Materials
AI: Learn about designing AI in UE
Material: Start Material
Player: Add data structure for Materials.
Game Mode: Add data structure for Materials.
2/7 - 2/14
Mapping: Add light sources to the level. Find a free texture asset and apply textures to ground and walls.
Create AI behavior tree.
2/14 - 2/21
Mapping: Add details, create interactable envrionments (open/close door), add ambient sounds, etc.
Finish Material, Start Minor Objective
2/21 - 2/28
2/28 - 3/4
3/4 - 3/7
Finish Minor Objective, Start Trap
3/7 - 3/14
3/14 - 3/21
3/21 - 3/28
Finish Trap, Start Weapon
3/28 - 4/4
4/4 - 4/11
4/11 - 4/18
Finish Game
4/18 - **4/23**
Test Final Game, download to other PC's/laptops, determine how to present at conference