## Sheet1
Materials, Traps, Weapons, Minor Objectives will probably have definitive start and end tasks. Player and AI classes will probably be continuously updated to integrate the other objects.
Week | Development Plan | Assigned To | Test and Demonstration Plan
1/24 - 1/31
Set up an Unreal Engine project with source control
|  | Kenny | Created and initialized UE project. Pushed to GitHub
|  | Tony | Pulled project, added sphere to project. Pushed to GitHub.
|  | Nick | Pulled project, modified C++ files. Pushed to GitHub.
|  | Roger | Pulled project, added pillars to project. Pushed to GitHub.
| Make a bird's eye view of the level. | Nick
1/31 - 2/7
| Start building the level according to the bird's eye view. | Nick | Game demonstration of sculpted landscape.
Present bird's-eye view diagram of level.
| Add skeletal mesh to player pawn; update project defaults to select game mode and pawn. | Tony | Screenshot of skeletal mesh attached to player pawn.
| Make player pawn move around and jump. | Roger | Game demonstration.
| Create AI pawn. Have it follow player. | Kenny | Game demonstration.
2/7 - 2/14
| Create a Material, have player be able to walk over and interact with it | Kenny | Output log when walking over
| Implement basic AI Behavior Tree |  | Screenshot
| Animate Player and AI models |  | Game demonstration
| Add details, lighting, etc. to map. | Nick | Present screenshot of UE bird's-eye view of the map
(to showcase area divisions). Also game demonstration.
2/14 - 2/21
| Expand AI Behavior Tree to scout for material locations | Roger
| Implement a check for materials when player is in crafting location, allow materials to respawn if "dropped" | Kenny
| Start minor objectives | Anthony
| Add details, lighting, etc. to map | Nick
2/21 - 2/28
2/28 - 3/4
3/4 - 3/7
Finish Minor Objective, Start Trap
3/7 - 3/14
3/14 - 3/21
3/21 - 3/28
Finish Trap, Start Weapon
3/28 - 4/4
4/4 - 4/11
4/11 - 4/18
Finish Game
4/18 - **4/23**
Test Final Game, download to other PC's/laptops, determine how to present at conference